## Gantt Chart
AI Arabic Morphosyntactic Explorer — Monthly Execution Plan
Sprint: 31 March 2026 – 19 April 2026 ¦ 30-Day Fellowship Development Plan
[5 empty] | March 2026 | April 2026
Phase | Task / Deliverable | Start | End | Days | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
[5 empty] | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Phase 1: Setup & Infrastructure | Environment & Docker Setup | 2026-03-31 | 2026-04-02 | 3 | bar: T to T
| Dataset Acquisition & Preparation | 2026-04-01 | 2026-04-04 | 4 | bar: T to S; M to F; M to F
| System Architecture Design | 2026-04-02 | 2026-04-03 | 2 | bar: T to F
Phase 2: NLP & Backend | CAMeL Tools NLP Integration | 2026-04-04 | 2026-04-08 | 5 | bar: T to F; M to F
| FastAPI Backend Development | 2026-04-05 | 2026-04-10 | 6 | bar: S to F
| ChromaDB Vector Database Setup | 2026-04-06 | 2026-04-09 | 4 | bar: T to F; M to F; M to F
Phase 3: AI & RAG Pipeline | Gemini 3.1 Flash Lite API Integration | 2026-04-09 | 2026-04-12 | 4 | bar: T to S
| RAG Pipeline Implementation | 2026-04-10 | 2026-04-14 | 5 | bar: T to F; M to F
| Context Caching Setup | 2026-04-12 | 2026-04-14 | 3 | bar: S to T
Phase 4: Frontend & Deployment | React Native RTL UI Build | 2026-04-14 | 2026-04-17 | 4 | bar: T to F; M to F; M to F
| Integration Testing & QA | 2026-04-15 | 2026-04-17 | 3 | bar: W to F
| Containerised Deployment | 2026-04-17 | 2026-04-18 | 2 | bar: T to F; M to F; M to S
| ◆ MILESTONE — Project Delivery | 2026-04-19 | 2026-04-19 | 1 | bar: S
Legend: |  |  |  |  | W: Phase 1: Setup & Infrastructure; S: Phase 2: NLP & Backend; T: Phase 3: AI & RAG Pipeline; F: Phase 4: Frontend & Deployment; M: Milestone; T: Weekend

## Execution Plan
AI Arabic Morphosyntactic Explorer — Monthly Execution Plan
Sprint: 31 March 2026 – 19 April 2026 ¦ 30-Day Fellowship Development Plan
PROJECT OVERVIEW
Project Name | AI Arabic Morphosyntactic Explorer (A-AME)
Purpose | A real-time AI-driven pedagogical tutor for Classical (Quranic) Arabic — a 'Linguistic Co-pilot' bridging complex linguistics and modern learners.
Scope | Word-level morphological analysis, AI-assisted I'rab (syntax) explanations via RAG, grounded on verified Quranic datasets.
Exclusions | Full translation, non-Quranic text processing, offline AI functionality.
Timeline | 31 March – 19 April 2026 (20-day active sprint)
Constraints | 30-day deadline, external API dependency (Gemini 3.1 Flash Lite), limited compute resources, dataset coverage.
KEY OBJECTIVES
# | Objective | Description
1 | High-Fidelity Reasoning | LLM-powered explanations of I'rab (syntax) and Sarf (morphology) for Quranic text.
2 | Grounded Accuracy | RAG pipeline grounded in expert-verified datasets (QAC, MASAQ, Quran-MD) to prevent hallucination.
3 | Professional Deployment | Containerised Docker backend paired with a mirrored RTL React Native mobile application.
4 | Cost Efficiency | Gemini 3.1 Flash Lite context caching targeting a 75% reduction in API operational costs.
PHASE EXECUTION PLAN
Phase | Deliverable / Task | Start | End | Days | Notes
Phase 1: Setup & Infrastructure
| Environment & Docker Setup | Mar 31 | Apr 2 | 3 | Configure containers, dev environment, CI/CD pipeline.
| Dataset Acquisition & Preparation | Apr 1 | Apr 4 | 4 | Download & preprocess QAC, MASAQ, and Quran-MD datasets.
| System Architecture Design | Apr 2 | Apr 3 | 2 | Define API schema, database schema, and component boundaries.
Phase 2: NLP & Backend Core
| CAMeL Tools NLP Integration | Apr 4 | Apr 8 | 5 | Root extraction, POS tagging, morphological segmentation.
| FastAPI Backend Development | Apr 5 | Apr 10 | 6 | Build REST endpoints for word-level analysis.
| ChromaDB Vector Database Setup | Apr 6 | Apr 9 | 4 | Ingest Quranic segments with linguistic metadata tags.
Phase 3: AI & RAG Pipeline
| Gemini 3.1 Flash Lite API Integration | Apr 9 | Apr 12 | 4 | Connect Gemini 3.1 Flash Lite for pedagogical reasoning & tutoring.
| RAG Pipeline Implementation | Apr 10 | Apr 14 | 5 | Retrieval-Augmented Generation over verified Quranic corpus.
| Context Caching Setup | Apr 12 | Apr 14 | 3 | Implement caching layer targeting ~75% API cost reduction.
Phase 4: Frontend & Deployment
| React Native RTL UI Build | Apr 14 | Apr 17 | 4 | Expo app with full Right-to-Left Arabic layout and API integration.
| Integration Testing & QA | Apr 15 | Apr 17 | 3 | End-to-end testing, bug fixes, and performance validation.
| Containerised Deployment | Apr 17 | Apr 18 | 2 | Docker build, deployment pipeline, and environment hardening.
| ◆ Project Delivery (Milestone) | Apr 19 | Apr 19 | 1 | Final submission — all deliverables handed over.
TECHNOLOGY STACK
Layer | Technology | Purpose
Reasoning Layer | Gemini 3.1 Flash Lite API | Pedagogical logic, conversational tutoring, I'rab explanations.
NLP Layer | CAMeL Tools (NYU Abu Dhabi) | Morphological parsing, root identification, POS tagging.
Knowledge Layer | ChromaDB Vector Database | Stores Quranic segments with extensive linguistic metadata.
Interface Layer | React Native (Expo) + RTL | Mobile-first mirrored UI with full Arabic Right-to-Left support.
Backend Layer | FastAPI + Docker | REST API server; containerised for reproducible deployment.
DATASETS
Dataset | Description
Quranic Arabic Corpus (QAC) | Morphological word-by-word data and tags — gold standard for verified Quranic data.
MASAQ Dataset (2025) | High-quality morphosyntactically annotated Quran corpus.
Quran-MD Dataset | Multimodal Quranic dataset with word-level audio and linguistic alignment.